## Dashboard
PROJECT PLAN AND GANTT CHART©
PROJECT NAME: | LaunchOceanside
DATE: | 2024-05-22
Update: | 2024-10-25
Copyright 2024 by Dr. Paul M. Wendee. All Rights Reserved.

## Instructions
Instructions
I have included a workbook that I am using for a Rotary project for my Oceanside Rotary Club, called LauchOceanside. This is to make it easier for you to follow the instructions listed in this section.
While not completely necessary, some familiarity with Microsoft Excel will be helpful. In any event, following the examples in this sample workbook for
LaunchOcenside should be sufficient to create your own Project Plan and Gantt Charts.
Ref: | LauchOceanside
Instructions
1. Fill in the information on the Dashboard tab. You may add additional information and/or include summary data from the other worksheets in this workbook in the Dashboard.
2. Enter your data in the Data tab section of this workbook.
3. The Gantt Chart should automatically update when you enter data in the Data tab; but you may have to adjust it somewhat. If you are not familiar with Microsoft Excel,
you can do a Google search to get help.
4. The first part of the Resources tab is linked to the Data tab. It should automatically update when you enter data in the Data tab; but you may have to adjust it somewhat.
5. You can add additional tabs, such as the Micro Loans and Budget tabs that we have added in this workbook.

## Data
|  | End | Start on
Task | Start Date | Date | Day | Duration
Start Project | 2024-02-06 | 2024-02-16 |  | 11
Contact LaunchRaleigh | 2024-02-06 | 2024-02-07 |  | 2
Initial Planning and Ideation | 2024-02-06 | 2024-02-19 |  | 14
Board Approval | 2024-04-12 | 2024-04-13 |  | 2
Recruit Volunteers | 2024-02-24 | 2024-10-31 |  | 251
Detailed Planning | 2024-05-22 | 2024-10-31 |  | 163
Community Needs Assessment | 2024-02-06 | 2024-02-16 |  | 11
Structure as a Social Enterprise | 2024-09-15 | 2024-10-31 |  | 47
Presentation to Club | 2024-05-30 | 2024-05-31 |  | 2
Poverty, Inc. | 2024-09-30 | 2024-10-15 |  | 16
Set up foundation account (e.g., Goat for Joe) | 2024-09-15 | 2024-09-30 |  | 16
Budget* | 2024-07-18 | 2025-01-05 |  | 172
Team Research Elements | 2024-09-03 | 2024-09-30 |  | 28
~Budget | 2024-09-03 | 2024-09-30 |  | 28
~LaunchMyCity Items | 2024-09-03 | 2024-09-30 |  | 28
Register Domain Name | 2024-09-03 | 2024-09-30 |  | 28
Launch Website | 2024-10-07 | 2024-11-15 |  | 40
Press Release | 2024-11-15 | 2025-01-05 |  | 52
Ad in District 530 Directory | 2024-10-10 | 2024-11-01 |  | 23
Engage Resources* | 2024-07-09 | 2025-01-05 |  | 181
Recruit Community Partners | 2024-09-03 | 2025-01-05 |  | 125
~SBA | 2024-09-03 | 2025-01-05 |  | 125
~SCORE | 2024-09-03 | 2025-01-05 |  | 125
Contact Kaufman FastTrac or Other | 2024-09-03 | 2025-01-05 |  | 125
Paul Get Certified as an Instructor | 2024-09-03 | 2025-01-05 |  | 125
Business Power Tools | 2024-07-18 | 2025-01-05 |  | 172
Find Training Location | 2024-09-03 | 2025-01-05 |  | 125
Information Meetings (See LaunchRaleigh Timeline) | 2024-09-03 | 2025-01-05 |  | 125
Recruit Mentors | 2024-07-18 | 2025-01-05 |  | 172
Review $1 Million Cups for Collaboration | 2024-10-23 | 2025-01-05 |  | 75
Recruit Instructors | 2024-07-18 | 2025-01-05 |  | 172
Campaign to Promote the Program | 2024-09-03 | 2025-01-05 |  | 125
Recruit Companies | 2024-09-03 | 2025-01-05 |  | 125
Form Selection Committee | 2024-09-03 | 2025-01-05 |  | 125
Announce Company Recruitment | 2024-09-03 | 2025-01-05 |  | 125
Matrix for Company Selection | 2024-09-03 | 2025-01-05 |  | 125
Plan and Hold Information Sessions | 2024-09-03 | 2025-01-05 |  | 125
Pitch Contest | 2024-10-31 | 2024-11-30 |  | 31
Select Companies | 2024-10-31 | 2024-11-30 |  | 31
Micro-Loans* | 2024-09-09 | 2025-01-05 |  | 119
Identify What Loans We Plan to Offer | 2024-09-09 | 2025-01-05 |  | 119
Contact KIVA | 2024-09-09 | 2024-10-31 |  | 53
Get Food Donations | 2024-11-05 | 2025-01-28 |  | 85
Secure Mentors - 6 month commitment | 2024-07-18 | 2025-01-05 |  | 172
First Cohort Start | 2025-01-27 | 2025-01-28 |  | 2
Week 1 - Orientation | 2025-01-27 | 2025-01-28 |  | 2
Week 2 - Class | 2025-02-03 | 2025-02-04 |  | 2
Week 3 - Class | 2025-02-10 | 2025-02-11 |  | 2
Week 4 - Class | 2025-02-17 | 2025-02-18 |  | 2
Week 5 - Class | 2025-02-24 | 2025-02-25 |  | 2
Week 6 - Class | 2025-03-03 | 2025-03-04 |  | 2
Week 7 - Class | 2025-03-10 | 2025-03-11 |  | 2
Week 8 - Class | 2025-03-17 | 2025-03-18 |  | 2
Week 9 - Class | 2025-03-24 | 2025-03-25 |  | 2
Week 10 - Graduation | 2025-03-31 | 2025-04-01 |  | 2
Team Planning Meetings | 2024-06-01 | 2025-06-30 |  | 395

## Resources
RESOURCES
Non-Linked Resources:
Task | People | Materials | Place | People | Materials | Place | What
Start Project | Paul |  |  | Paul |  |  | Project Manager
Contact LaunchRaleigh | Paul |  |  | Renee |  |  | Chief of Staff
Initial Planning and Ideation | Paul
Board Approval | Paul, Renee
Recruit Volunteers | Paul
Detailed Planning | Paul
Community Needs Assessment | Paul
Structure as a Social Enterprise | Paul
Presentation to Club | Paul, Renee
Poverty, Inc. | Paul
Set up foundation account (e.g., Goat for Joe) | Paul
Budget* | Paul
Team Research Elements | As Assigned
~Budget
~LaunchMyCity Items
Register Domain Name
Launch Website | Paul
Press Release | Paul
Engage Resources*
Recruit Community Partners
~SBA
~SCORE
Contact Kaufman FastTrac or Other | Paul
Paul Get Certified as an Instructor | Paul
Business Power Tools | Paul
Find Training Location | Paul
Recruit Mentors
Recruit Instructors
Campaign to Promote the Program
Recruit Companies
Form Selection Committee
Announce Company Recruitment
Matrix for Company Selection
Plan and Hold Information Sessions
Pitch Contest
Select Companies
Micro-Loans*
Identify What Loans We Plan to Offer
Contact KIVA
Get Food Donations
Secure Mentors - 6 month commitment
First Cohort Start
Week 1 - Orientation
Week 2 - Class
Week 3 - Class
Week 4 - Class
Week 5 - Class
Week 6 - Class
Week 7 - Class
Week 8 - Class
Week 9 - Class
Week 10 - Graduation
Team Planning Meetings

## Micro Loans
MICRO-LOANS
LaunchMyCity recommends KIVA

## Budget
BUDGET
Revenue
Advances Renee
Advances Paul | 134.69
Total | 134.69
Expenses
District Directory Ad |  | Paid by Renee
Domani Name | 15.17 | Paid by Paul
Website Hosting | 119.52
Secure Website Service
Total | 134.69
Net Difference | 0